## Contoh
ILLUSTRATIVE EXAMPLES ON PREPARATION OF IFRS 9 IMPLEMENTATION
Bank 123 Ltd.
The following table is an illustrative example. The Bank prepares a roadmap in accordance with conditions of eash bank's circumstances, with keep attemtion to deadlines of each stage so that the implementation target of January 1st, 2020 can be achieved
| Documents Attached | 2017 (the…month) |  |  |  | 2018 (The…month) | [11 empty] | 2019 (The…month) | [11 empty] | 2020
|  | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1
Stage I : Initial Preparation (no later than Q4/2017)
1. Discussions with Board of Commissioners, Directors, Audit Committee, and related Working units | Minutes of Meeting
2. Training and socialization of the application of PSAK 71 to related work units | Training schedule and realization
3. Setting up the Task Force and work programs in detail including timeline and targets | BoD's Decree and action plan details | bar: 2018 (The…month) 11
4. Preparation of RBB (bank Business Plan) that taking into account additional costs for IFRS 9 implementation | bar: 2018 (The…month) 11
*) adjustment, if any
Tahap II: Gap analysis (no later than Q I/2018)
Gap Analysis on classification and measurement | 1) Results of Quantitative and Qualitative Studies on Classification and Measurement of Financial Instruments; 2) improvements proposal on the business model and resources
1. Solely Payment of Principal and Interest test (SPPI test) * | bar: 2018 (The…month) 1 to 2018 (The…month) 3
2. Business Model Review | bar: 2018 (The…month) 1 to 2018 (The…month) 3
3. The adequacy of resources (i.e human, funds, infrastructiure, policies and procedures) | bar: 2018 (The…month) 1 to 2018 (The…month) 3
Gap Analysis on Impairment
1. Identify a potentially impaired financial assset | 1) Results of Quantitative and Qualitative studies on impairment of financial instruments 2) Improvements proposal in credit risk indicators (i.e. internal ratings and impairment indicators) as well as resources | bar: 2018 (The…month) 1 to 2018 (The…month) 3
2. Mapping internal ratings with indicators of impairment requirements under PSAK 71 | bar: 2018 (The…month) 1 to 2018 (The…month) 3
3. The adequacy of resources (i.e human, funds, infrastructiure, policies and procedures) | bar: 2018 (The…month) 1 to 2018 (The…month) 3
Gap Analysis on Hedge Accounting (Optional)
1. Review on existing derivative transanction and hedging needs | 1) Results of Quantittative and Qualitative studies on hedge accounting (for banks that are not actively involve on hedging, the analysis can be simplified) 2) Improvement proposal on market risk management and resources | bar: 2018 (The…month) 1 to 2018 (The…month) 3
2. Reviewing the existence of risk management and compare with hedge accounting in accordance to PSAK 71 | bar: 2018 (The…month) 1 to 2018 (The…month) 3
3. Notice at the need to change existing hedge accounting (in accordance with PSAK 55) with hedge accounting under PSAK 71 | bar: 2018 (The…month) 1 to 2018 (The…month) 3
3. The adequacy of resources (i.e human, funds, infrastructiure, policies and procedures) | bar: 2018 (The…month) 1 to 2018 (The…month) 3
Tahap III: Development (no later than Q2/2018)
Development on Classification and Measurement
1. The Development of financial asset classification criteria based on SPPI | The policy draft on the classification of financial instruments, as well as contract (if required) | bar: 2018 (The…month) 4 to 2018 (The…month) 5
2. The Development on business model includes contract changes with thid parties, if required | bar: 2018 (The…month) 6 to 2018 (The…month) 9
3. Changes in policies and procediures | bar: 2018 (The…month) 8 to 2018 (The…month) 9
4. Adjustment on MIS for financial instruments, if required | Approval of changes on MIS and User requirement | bar: 2018 (The…month) 10 to 2018 (The…month) 12
5. Providing data/information required for disclosures in accordance to PSAK 71 | Draft of Disclosure on financial reports | bar: 2018 (The…month) 10 to 2018 (The…month) 12
Page 1 of 2
Development on Impairment
1. Building a model: | Models from PD, LGD, EAD that proposed and approved by BoD
a. Probability of Default (PD) | bar: 2018 (The…month) 4 to 2018 (The…month) 9
b. Loss Given Default (LGD) | bar: 2018 (The…month) 4 to 2018 (The…month) 9
c. Exposure at Default (EAD) | bar: 2018 (The…month) 4 to 2018 (The…month) 9
2. The development of a supporting system for the calculation of impairment: | 1)Proposal and approval of changes on MIS 2)User requirement 3)Progress report on the development MIS
a. Preparation of system design | bar: 2018 (The…month) 10 to 2018 (The…month) 12
b. Procurement system | bar: 2018 (The…month) 10 to 2018 (The…month) 12
c. Development system | bar: 2018 (The…month) 10 to 2018 (The…month) 12
3. System testing | Reports on the results of system testing
4. Adjustment on policies regarding IFRS 9 implementation including medium and long term contracts with third parties as well as off balance sheet elements | Draft of contract changes | bar: 2018 (The…month) 10 to 2018 (The…month) 12
5. The development on resources (i.e. human, funds infrastructure, policies and procedures) | 1) Draft of Policies, 2) Training realization | bar: 2018 (The…month) 10 to 2018 (The…month) 12
6. Providing data/information required for diclosure under PSAK 71 | Draft of disclosures on financial reports
Development on Hedge Accounting (Optional)
1. The development on risk management strategy and risk management objective (people, tools, and policies) in accordance to PSAK 71 | 1) Draft of policies regarding risk related (i.e.risk management and ALMA) 2) SOP Draft on Hedge Accounting | bar: 2018 (The…month) 4 to 2018 (The…month) 8
2. The development of accounting for risk management activity in accordance to PSAK 71 | bar: 2018 (The…month) 9
3. The development of hedge effective test (include economic relationship, credit risk does not dominate dan hedge ratio) in accordance to PSAK 71 | bar: 2018 (The…month) 10 to 2018 (The…month) 11
4. Adjustment on MIS (if required) | The Approval and the development of MIS (if required) | bar: 2018 (The…month) 12
5. Providing data/information required for disclosures under PSAK 71 | Draft of disclosures on financial reports | bar: 2018 (The…month) 10 to 2018 (The…month) 11
Tahap IV: Final Preparation dan parallel run (at least in 6 months)
1. Finalization (MIS PSAK 71) | Minutes of Meeting
2. Approval of changes on Policies and Procedures as well as related Business Process (i.e. Accounting, Credit, Treasury, Risk Management) | A letter of approval of policies and procedures
3. Parallel run | Parallel run analysis report, as well as the improvements (if required)
Go Live | Implementation reports of PSAK 71
Page 2 of 2