## Web OJK
Issue # | Initiator | Date Opened | Summary Description | Impact/ Importance | Type | Owner | Target Completion Date | Current Status | Completion Date | Resolution
1
2
Note on A1: sequential numbering of issues as they are logged works best
Note on B1: name of the initiator and their contact number
Note on C1: date and time stamp when the question or issue was raised (not the date it was logged in case there was a delay in logging it)
Note on D1: describe the question or issue in enough detail for others referencing the log to understand it
Note on E1: select prioritization of the issue based on its impact and importance: low – issue that needs to be addressed but does not impact going live or the timeline to complete the cutover tasks medium – does not prevent going live, but a work around may be needed and the cutover timeline may be impacted, therefore address promptly high – critical issue impacting both cutover and ability to go live, address immediately
Note on F1: select the nature of the issue from the list defined. Edit the list via Data --> Validation from the toolbar.
Note on G1: assign individual who is responsible for taking the next step to resolve the issue
Note on H1: date that resolution is targeted to be completed
Note on I1: indicates standing of the issue overall (not from the individual’s responsibility perspective)
Note on J1: when current status is updated to ‘closed’ indicate the date that it was resolved, documented and communicated
Note on K1: when current status is updated to ‘closed’ document the resolution defined

## APU-PPT
Issue # | Initiator | Date Opened | Summary Description | Impact/ Importance | Type | Owner | Target Completion Date | Current Status | Completion Date | Resolution
1 | Gista | 7 Okt | Redirect breadcrumb / navigasi menu ke list teratas sub menunya | Medium | Other | Aldrian | 8 Okt | Open
2 | Gista | 7 Okt | Pasang form, captcha dan tarik info kontak untuk halaman hubungi kami | High | Functionality/usage | Aldrian | 8 Okt | Open
3 | Gista | 7 Okt | Hilangkan preview di halaman hasil search | Medium | Other | Aldrian | 8 Okt | Open
4 | Gista | 7 Okt | Tampilan di mobile view untuk browser safari dan chrome di iPhone 5S masih belum muncul menunya | Medium | Interface | Kiki | 8 Okt | In Process
5 | Gista | 7 Okt | Tampilan list My Task belum rapih | Low | Interface | Kiki | 8 Okt | Open
Note on A1: sequential numbering of issues as they are logged works best
Note on B1: name of the initiator and their contact number
Note on C1: date and time stamp when the question or issue was raised (not the date it was logged in case there was a delay in logging it)
Note on D1: describe the question or issue in enough detail for others referencing the log to understand it
Note on E1: select prioritization of the issue based on its impact and importance: low – issue that needs to be addressed but does not impact going live or the timeline to complete the cutover tasks medium – does not prevent going live, but a work around may be needed and the cutover timeline may be impacted, therefore address promptly high – critical issue impacting both cutover and ability to go live, address immediately
Note on F1: select the nature of the issue from the list defined. Edit the list via Data --> Validation from the toolbar.
Note on G1: assign individual who is responsible for taking the next step to resolve the issue
Note on H1: date that resolution is targeted to be completed
Note on I1: indicates standing of the issue overall (not from the individual’s responsibility perspective)
Note on J1: when current status is updated to ‘closed’ indicate the date that it was resolved, documented and communicated
Note on K1: when current status is updated to ‘closed’ document the resolution defined

## Keuangan Berkelanjutan
Issue # | Initiator | Date Opened | Summary Description | Impact/ Importance | Type | Owner | Target Completion Date | Current Status | Completion Date | Resolution
1
Note on A1: sequential numbering of issues as they are logged works best
Note on B1: name of the initiator and their contact number
Note on C1: date and time stamp when the question or issue was raised (not the date it was logged in case there was a delay in logging it)
Note on D1: describe the question or issue in enough detail for others referencing the log to understand it
Note on E1: select prioritization of the issue based on its impact and importance: low – issue that needs to be addressed but does not impact going live or the timeline to complete the cutover tasks medium – does not prevent going live, but a work around may be needed and the cutover timeline may be impacted, therefore address promptly high – critical issue impacting both cutover and ability to go live, address immediately
Note on F1: select the nature of the issue from the list defined. Edit the list via Data --> Validation from the toolbar.
Note on G1: assign individual who is responsible for taking the next step to resolve the issue
Note on H1: date that resolution is targeted to be completed
Note on I1: indicates standing of the issue overall (not from the individual’s responsibility perspective)
Note on J1: when current status is updated to ‘closed’ indicate the date that it was resolved, documented and communicated
Note on K1: when current status is updated to ‘closed’ document the resolution defined

## FSAP
Issue # | Initiator | Date Opened | Summary Description | Impact/ Importance | Type | Owner | Target Completion Date | Current Status | Completion Date | Resolution
1
Note on A1: sequential numbering of issues as they are logged works best
Note on B1: name of the initiator and their contact number
Note on C1: date and time stamp when the question or issue was raised (not the date it was logged in case there was a delay in logging it)
Note on D1: describe the question or issue in enough detail for others referencing the log to understand it
Note on E1: select prioritization of the issue based on its impact and importance: low – issue that needs to be addressed but does not impact going live or the timeline to complete the cutover tasks medium – does not prevent going live, but a work around may be needed and the cutover timeline may be impacted, therefore address promptly high – critical issue impacting both cutover and ability to go live, address immediately
Note on F1: select the nature of the issue from the list defined. Edit the list via Data --> Validation from the toolbar.
Note on G1: assign individual who is responsible for taking the next step to resolve the issue
Note on H1: date that resolution is targeted to be completed
Note on I1: indicates standing of the issue overall (not from the individual’s responsibility perspective)
Note on J1: when current status is updated to ‘closed’ indicate the date that it was resolved, documented and communicated
Note on K1: when current status is updated to ‘closed’ document the resolution defined